## Forward Traceability
Requirements | Tests | Executions | Defects
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-42 - Verify that the Save button can be clicked after completing the mandatory fields and a new Vacancy is added | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs - 1 defect | TIB-19 - Verify that the Job Title is a mandatory field | Vacancies Functionality Tests - FAIL | TIB-62 - Done - [Recruitment][Add] Save button is active by default
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-20 - Verify that the Vacancy Name field is mandatory | Vacancies Functionality Tests - FAIL | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-24 - Verify that the Hiring Manger is a mandatory field | Vacancies Functionality Tests - FAIL | None
TIB-2 - As an user I want to be able to to create vacancy jobs - 1 defect | TIB-63 - Verify that a vacancy job can be created having any name at hiring manager field | Vacancies Functionality Tests - FAIL | TIB-64 - Done - [Recruitment][Add] Hiring Manager field doesn't accept any names
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-3 - Verify that a vacancy job can be searched with all field set to All | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-4 - Very that a vacancy job can be searched with any value in Job Title field and All in the other fields | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-5 - Verify that a vacancy job can be searched with any value in Vacancy field and All in the other fields | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-6 - Verify that a vacancy job can be searched with any value in Hiring Manager fields and All in the other fields | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-7 - Verify that a vacancy job can be searched with any value in Status field | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-8 - Verify that a vacancy job can be searched with any value in the fields: Job Title, Vacancy, Hiring Manager, Status | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs - 1 defect | TIB-9 - Verify that the Reset button resets the Job Title if it has other than 'All' value and the other fields have 'All' | Vacancies Functionality Tests - FAIL | TIB-60 - Done - [Recruitment] Reset button reloads the page
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-10 - Verify that the Reset button resets the Vacancy if it has other than 'All' value | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-11 - Verify that the Reset button resets the Hiring Manager if it has other than 'All' value | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-12 - Verify that the Reset button resets the Status field if it has other than 'All' value | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-13 - Verify that the Reset button resets all the fields if their values are different from 'All' | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-14 - Verify that the Add button can be clicked | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-16 - Verify that multiple vacancy jobs can be deleted by checking the box next to the Vacancy job name | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs - 1 defect | TIB-17 - Verify that a vacancy job can be created by completing all the mandatory fields | Vacancies Functionality Tests - FAIL | TIB-59 - Done - [Recruitment][Add] Edit job vacancy page is displayed after after saving a new job vacancy
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-18 - Verify that a vacancy job can be created with any Job Title and completing the rest of the mandatory fields | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-21 - Verify that the Vacancy Name accepts a total of 55 characters maximum length | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-22 - Verify that the Vacancy Name accepts any type of characters | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs - 1 defect | TIB-23 - Verify that the Vacancy Name doesn't accept more than 55 characters | Vacancies Functionality Tests - FAIL | TIB-57 - Done - [Vacancies][Add] 56 characters can be inserted into Vacancy Name field
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-25 - Verify that the Hiring Manager field accepts a maximum of 55 characters | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-26 - Verify that the Hiring Manager field accepts only letters. | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-27 - Verify that the Hiring Manager field doesn't accept more than 55 characters | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-28 - Verify that the Number of Positions is not a mandatory field | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-29 - Verify that the Number of Positions accepts a total number of 2 numerical maximum length | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-30 - Verify that the Number of Positions doesn't accept more than 2 numerical characters | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs - 1 defect | TIB-31 - Verify that the Number of Positions doesn't accept other characters than numerical | Vacancies Functionality Tests - FAIL | TIB-61 - Done - [Recruitment][Add] White space can be inserted into number of positions field
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-32 - Verify that the Description is not a mandatory field | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-33 - Verify that the Description accepts a total 500 character maximum length | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-34 - Verify that the Description accepts any type of character | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs - 1 defect | TIB-35 - Verify that the Description doesn't accept more than 500 character maximum length | Vacancies Functionality Tests - FAIL | TIB-58 - Done - [Recruitment][Add] More than 500 characters can be written in description
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-36 - Verify that the Active checkbox is checked by default | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-37 - Verify that the Published in RSS feed and web page checkbox is checked by default | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-38 - Verify that the Active checkbox can be unchecked | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-41 - Verify that the RSS Feed URL link redirect to the RSS Feed page | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-44 - Verify that all the Vacancies can be deleted by checking the box new to 'Vacancy' | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-46 - Verify that clicking on a vacancy job the user is redirected to edit the job | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-47 - Verify that the Job Title can be changed | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-48 - Verify that the vacancy name can be changed | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-49 - Verify that the Hiring manager can be changed | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-50 - Verify that the status can be changed | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-51 - Verify that the number of positions can be changed | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs - 1 defect | TIB-52 - Verify that the description can be changed | Vacancies Functionality Tests - FAIL | TIB-56 - Done - [Vacancies][Edit] Extra step to click an edit button to actual reach the editable page
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-53 - Verify that the publish in RSS feed and web page checkbox can be unchecked | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-54 - Verify that clicking the Save button will save the changes | Vacancies Functionality Tests - PASS | None
TIB-2 - As an user I want to be able to to create vacancy jobs | TIB-55 - Verify that the Cancel button will no change anything to the job | Vacancies Functionality Tests - PASS | None